AIHW Recidivism Project

Background

In 2009, the AJJA funded the Australian Institute of Criminology to develop principles for measuring juvenile recidivism in Australia. The resulting report, Richards (2010) Recidivism outcomes for juveniles in Australia: a national research project recommends that the severity of recidivism be measured as well as the overall amount of recidivism.

Stage 1

SCCDSAC has funded ($97, 625) the AIHW for stage 1 of the development of a data collection to measure juvenile recidivism. Stage 1 involves:

- exploring the extent to which juvenile recidivism can be analysed using the existing JJ NMDS

- assessing whether data items additional to those already in the JJ NMDS are required

- analysing available offence date data to determine whether it should be implemented in the JJ NMDS.

To date, NSW and Qld have provided pilot data on offence date. The AIHW has begun analysing both the pilot data and the existing JJ NMDS data and it is anticipated that a draft report will be provided to the AJJA in May 2013 and to SCCDSAC in June 2013.

Stage 2

The AIHW has applied for funding from SCCDSAC’s 2013-14 budget ($131,200) to further develop the project.

Future stages will involve piloting and analysing additional data items that were identified in Stage 1 as required for a data collection to measure juvenile recidivism, including offence type and severity and data on progression to the adult system.