## CP YJ data linkage
CP YJ data linkage development project
Activity/milestone | Expected completion | Payment (excl GST) | Total payment 13-14 | 161800
Receive SCCDSAC approval and 2013–14 funding | 2013-09-01 |  | Total payment 14-15 | 83700
Progress noted in RIG report to AJJA (Nov meeting) | 2013-09-01
Establish reference group | 2013-10-01 | 80900
Progress report 1 to project control group | 2014-01-01
Review previous linkage project and identify and pilot any additional data items required for successful linkage | 2014-01-01
Progress report 2 to project control group | 2014-04-01
Apply for SCCDSAC 2014–15 funding | 2014-06-01 | 80900
Progress report 3 to project control group | 2014-07-01
Progress noted in RIG report to AJJA (Nov meeting) | 2014-09-01
Develop a method to link the data collections on an annual basis | 2014-09-01
Progress report 4 to project control group | 2014-10-01 | 41850
Progress report 5 to project control group | 2015-01-01
Identify key questions to be answered by a linked data set in consultation with the reference group | 2015-01-01
Progress report 6 to project control group | 2015-04-01
Develop standard analysis and reporting on the linked data set | 2015-05-01
Progress report 7 to project control group | 2014-07-01 | 41850
Final report to project control group, AJJA and SCCDSAC | 2015-09-01
Note on C3: Author: Payments made in June and November - allocated in this column to nearest event.