## Youth Recidivism Stage 2
Youth recidivism stage 2: offence severity
Activity/milestone | Expected completion | Payment (excl GST) | Total payment | 131200
Receive SCCDSAC approval and funding | 2013-09-01
Progress noted in RIG report to AJJA (Nov meeting) | 2013-10-01
Establish reference group and confirm scope | 2013-10-01 | 65600
Review existing classification systems | 2013-12-01
Progress report 1 to project control group | 2014-01-01
Progress report 2 to project control group | 2014-04-01
Progress noted in RIG report to AJJA (May meeting) | 2014-04-01
Analyse existing offence data and develop classification of offence severity in consultation with reference group | 2014-04-01
Progress report 3 to project control group | 2014-07-01 | 65600
Develop recommendations in consultaton with reference group | 2014-07-01
Final report to project control group, AJJA and SCCDSAC | 2014-10-01
Note on C3: Author: Payments made in June and November - allocated in this column to nearest event.